## Sheet1
Task ID | Tasks | Effort (hrs) approxmation | Duration (days) approxmation | Dependent tasks | resources used | status
PP_DOC_1 | creating project plan doc | 3 | 2 | RSK_DOC_4, PS_DOC_2 , ISSUES_DOC_5 , PT_DOC_10 , SIQ_DOC_8 , CM_DOC_3 |  | done
PS_DOC_2 | creating project schedule | 2 | 1 |  |  | done
CM_DOC_3 | configuration management (CM) tool | 3 | 2 |  | Git technology , github.com | done
RSK_DOC_4 | Risk sheet | 2 | 2 | SRS_DOC_6 |  | done
ISSUES_DOC_5 | Issues sheet | 2 | 1 |  |  | done
SRS_DOC_6 | system requirements specifications (SRS) | 4 | 3 |  |  | in progress
RTM_DOC_7 | requirements traceability matrix (RTM) |  |  | SRS_DOC_6 |  | not done
SIQ_DOC_8 | software interactive questionnaire (SIQ) |  |  | SIQ_DOC_8 |  | in progress
SRSPR_DOC_9 | system requirements specifications (SRS) peer review sheet |  |  | SRS_DOC_6 |  | not done
PT_DOC_10 | project timeline | 2 | 1 | PS_DOC_2 | https://www.vertex42.com/Files/download2/gdrive.php?file=project-schedule | done