## Sheet1
Task ID | Tasks | Effort (hrs) approxmation | Duration (days) approxmation | Dependent tasks | Resources used | Status
Lhub_PP | Creating project plan doc | 3 | 2 | Lhub_RSK, Lhub_Sch , Lhub_Issue, Lhub_PT , Lhub_SIQ , Lhub_CMP |  | Done
Lhub_Sch | Creating project schedule | 2 | 1 |  |  | Done
Lhub_CMP | Configuration management (CM) plan | 3 | 2 |  | Git technology , github.com | Done
Lhub_RSK | Risk sheet | 2 | 2 | Lhub_SRS |  | Done
Lhub_Issue | Issues sheet | 2 | 1 | Lhub_SIQ |  | Done
Lhub_SRS | System requirements specifications (SRS) | 4 | 3 |  |  | Done
Lhub_RTM | Requirements traceability matrix (RTM) | 2 | 1 | Lhub_SRS |  | Done
Lhub_SIQ | Software interactive questionnaire (SIQ) | 1 | 3 | Lhub_SIQ |  | Done
Lhub_PR | System requirements specifications (SRS) peer review sheet | 2 | 3 | Lhub_SRS |  | Done
Lhub_PT | Project timeline | 2 | 1 | Lhub_Sch | https://www.vertex42.com/Files/download2/gdrive.php?file=project-schedule | Done
Lhub_SDD | Software design document (SDD) | 2 | 3 |  |  | Done
Lhub_DesignPR | design peer review sheet | 1 | 2 | Lhub_SDD