## Sheet1
Roles / Tasks | Mohamed Ragab ( project manager) | Mohamed Azmy | Aya Mohamed | Farah | Wafaa | Nada | Symbol | Meaning | notes
Week 1
Creating project plan document | A + C | C | C | R | C | R | R | Responsible
Creating project schedule | R | C | C | C | C | C | A | accountable
Configuration management (CM) plan | C | C | R | C | C | C | C | Consulted
Risk sheet | C | R | A | A | C | C | I | Informed | by default , all team members are informed regular when they frequently
Issues sheet | C | R | A | A | C | C
System requirements specifications (SRS) | C | A | C | C | R | C
Requirements traceability matrix (RTM) | A | C | R | C | C | C
Software interactive questionnaire (SIQ) | C | R | C | C | C | C |  | source that helped in creating this document | https://www.teamgantt.com/blog/raci-chart-definition-tips-and-example
System requirements specifications (SRS) peer review sheet | R | C | A | A | C | C
Week 2
Software design document (SDD) | C | C | R | C | C | C
Software design document peer review (Design PR) | A | C | R | C | C | C
Design the Entity Relationship Diagram (ERD)(Lhub_ERD) |  |  | R
design class diagram | C | C | C | R | C | C
design data flow diagram | C | C | C | C | C | R
design high level design | R | C | C | C | C | C
Use Case | C | C | C | C | R | C
Wire Frames | C | R | C | C | R | C
Week 3
develop "Login" page | C | C | R | C | C | C
develop "register" page | C | C | R | C | C | C
develop "forget password" page | C | C | R | C | C | C
develop "follow category" function | C | C | R | C | C | C
develop "search article" function | C | C | R | C | C | C
develop "navigate category " function | C | C | R | C | C | C
develop "search article" function | C | C | R | C | C | C
develop "review article" page (admin) | C | C | R | C | C | C
develop "Login" page (admin) | C | C | R | C | C | C
develop database | C | C | R | R | C | C
Week 4 (testing phase accoding to SRS)
2.4.1 Login Module | R | C | [6 empty] | the person who has "C" role will review the work of the "R" person
2.4.2 Registration Module | C | R
2.4.3 Homepage Module |  |  |  |  | C | R
2.4.4 Category Module | C |  |  |  | R
2.4.5 Review Articles Module |  |  |  | R |  | C