## Sheet1
Task ID | Tasks | Effort (hrs) approxmation | Duration (days) approxmation | Dependent tasks | Resources used | Status
Lhub_PP_V1 | Creating project plan doc | 3 | 2 | Lhub_RSK_V1, Lhub_Sch_V1 , Lhub_Issue_V1, Lhub_PT_V1 , Lhub_SIQ_V1 , Lhub_CMP_V1 |  | Done
Lhub_Sch_V1 | Creating project schedule | 2 | 1 |  |  | Done
Lhub_CMP_V1 | Configuration management (CM) plan | 3 | 2 |  | Git technology , github.com | Done
Lhub_RSK_V1 | Risk sheet | 2 | 2 | Lhub_SRS_V1 |  | Done
Lhub_ISSUE_V1 | Issues sheet | 2 | 1 | Lhub_SIQ_V1 |  | Done
Lhub_SRS_V1 | System requirements specifications (SRS) | 4 | 3 |  |  | Done
Lhub_RTM_V1 | Requirements traceability matrix (RTM) | 2 | 1 | Lhub_SRS_V1 |  | Done
Lhub_SIQ_V1 | Software interactive questionnaire (SIQ) | 1 | 3 | Lhub_SIQ_V1 |  | Done
Lhub_PR_V1 | System requirements specifications (SRS) peer review sheet | 2 | 3 | Lhub_SRS_V1 |  | Done
Lhub_PT_V1 | Project timeline | 2 | 1 | Lhub_Sch_V1 | https://www.vertex42.com/Files/download2/gdrive.php?file=project-schedule | Done