## Sheet1
roles / tasks | Mohamed Ragab ( project manager) | mohamed Azmy | Aya mohamed | farah | wafaa | nada | symbole | meaning | notes
Week 1
creating project plan doc | A + C | C | C | R | C | R | R | Responsible
creating project schedule | A+R | C | C | C | C | C | A | accountable
configuration management (CM) tool | C | C | A+R | C | C | C | C | Consulted
Risk sheet | C + R | A+R | C | C | C | C | I | Informed | by default , all team members are informed regulary when they frequently
Issues sheet | A + R | R | R | R | R | R
system requirements specifications (SRS) | C | A + R | C | C | R | C
requirements traceability matrix (RTM) | A + R | C | C | C | C | C
software interactive questionnaire (SIQ) | C | A + R | C | C | C | C |  | source that helped in creating this document | https://www.teamgantt.com/blog/raci-chart-definition-tips-and-example
system requirements specifications (SRS) peer review sheet | A+R | R | R | R | R | R