## Sheet1
Roles / Tasks | Mohamed Ragab ( project manager) | Mohamed Azmy | Aya Mohamed | Farah | Wafaa | Nada | Symbol | Meaning | notes
Week 1
Creating project plan document | A + C | C | C | R | C | R | R | Responsible
Creating project schedule | R | C | C | C | C | C | A | accountable
Configuration management (CM) plan | C | C | R | C | C | C | C | Consulted
Risk sheet | C | R | A | A | C | C | I | Informed | by default , all team members are informed regular when they frequently
Issues sheet | C | R | A | A | C | C
System requirements specifications (SRS) | C | A | C | C | R | C
Requirements traceability matrix (RTM) | A | C | R | C | C | C
Software interactive questionnaire (SIQ) | C | R | C | C | C | C |  | source that helped in creating this document | https://www.teamgantt.com/blog/raci-chart-definition-tips-and-example
System requirements specifications (SRS) peer review sheet | R | C | A | A | C | C