## Sheet1
Task ID | Tasks | Effort (hrs) approxmation | Duration (days) approxmation | Dependent tasks | resources used | status
Lhub_PP_V1 | creating project plan doc | 3 | 2 | Lhub_RSK_V1, Lhub_Sch_V1 , Lhub_Issue_V1, Lhub_PT_V1 , Lhub_SIQ_V1 , Lhub_CMP_V1 |  | done
Lhub_Sch_V1 | creating project schedule | 2 | 1 |  |  | done
Lhub_CMP_V1 | configuration management (CM) tool | 3 | 2 |  | Git technology , github.com | done
Lhub_RSK_V1 | Risk sheet | 2 | 2 | Lhub_SRS_V1 |  | done
Lhub_Issue_V1 | Issues sheet | 2 | 1 |  |  | done
Lhub_SRS_V1 | system requirements specifications (SRS) | 4 | 3 |  |  | done
Lhub_RTM_V1 | requirements traceability matrix (RTM) |  |  | Lhub_SRS_V1 |  | done
Lhub_SIQ_V1 | software interactive questionnaire (SIQ) |  |  | Lhub_SIQ_V1 |  | done
Lhub_PR_V1 | system requirements specifications (SRS) peer review sheet |  |  | Lhub_SRS_V1 |  | done
Lhub_PT_V1 | project timeline | 2 | 1 | Lhub_Sch_V1 | https://www.vertex42.com/Files/download2/gdrive.php?file=project-schedule | done